## Sheet1
Task ID | Task Description | Assigned To | Priority | Dependencies | Assigned Date | Expected Deadline | Estimated Time | Completed Date | Delay (days)
T1 | Fix critical security vulnerability in system | Charlie | High | No Dependency | 2024-01-23 | 2024-01-30 | 7 | 2024-01-30 | 0
T2 | Prepare financial report for Q1 | Eve | Medium | T1 | 2024-01-11 | 2024-01-15 | 4 | 2024-01-18 | 3
T3 | Schedule and conduct weekly team meeting | David | High | No Dependency | 2024-01-09 | 2024-01-11 | 2 | 2024-01-13 | 2
T4 | Submit project proposal before deadline | Bob | Medium | T1 | 2024-01-14 | 2024-01-22 | 8 | 2024-01-22 | 0
T5 | Review design documents and provide feedback | Charlie | Low | No Dependency | 2024-01-12 | 2024-01-13 | 1 | 2024-01-18 | 5
T6 | Update company website homepage with new content | David | Low | No Dependency | 2024-01-04 | 2024-01-05 | 1 | 2024-01-09 | 4
T7 | Resolve high-priority customer complaints | Eve | High | No Dependency | 2024-01-28 | 2024-02-05 | 8 | 2024-02-09 | 4
T8 | Analyze user feedback for product enhancements | Charlie | Urgent | No Dependency | 2024-01-18 | 2024-01-23 | 5 | 2024-01-27 | 4
T9 | Test new software release for bugs and stability | Eve | Medium | No Dependency | 2024-01-23 | 2024-01-24 | 1 | 2024-01-26 | 2
T10 | Conduct market research for upcoming product launch | Charlie | High | No Dependency | 2024-01-03 | 2024-01-06 | 3 | 2024-01-07 | 1
T11 | Optimize database queries for faster performance | Alice | Urgent | No Dependency | 2024-01-06 | 2024-01-10 | 4 | 2024-01-12 | 2
T12 | Develop machine learning model for sentiment analysis | Charlie | Medium | No Dependency | 2024-01-20 | 2024-01-22 | 2 | 2024-01-22 | 0
T13 | Write and review technical documentation | Alice | High | No Dependency | 2024-01-09 | 2024-01-16 | 7 | 2024-01-17 | 1
T14 | Improve CI/CD pipeline for automated deployments | Eve | Urgent | No Dependency | 2024-01-19 | 2024-01-26 | 7 | 2024-01-29 | 3
T15 | Monitor server performance and address downtime issues | Eve | Medium | T1 | 2024-01-01 | 2024-01-02 | 1 | 2024-01-03 | 1
T16 | Train new employees on company policies and procedures | Charlie | Low | No Dependency | 2024-01-01 | 2024-01-04 | 3 | 2024-01-07 | 3
T17 | Coordinate with vendors for procurement needs | David | Urgent | No Dependency | 2024-01-22 | 2024-01-29 | 7 | 2024-01-31 | 2
T18 | Create social media marketing strategy | Alice | High | No Dependency | 2024-01-03 | 2024-01-04 | 1 | 2024-01-06 | 2
T19 | Implement new security patches in infrastructure | Eve | High | No Dependency | 2024-01-01 | 2024-01-08 | 7 | 2024-01-10 | 2
T20 | Refactor legacy code for better maintainability | Bob | Low | No Dependency | 2024-01-04 | 2024-01-12 | 8 | 2024-01-13 | 1
T21 | Fix critical security vulnerability in system | David | Medium | No Dependency | 2024-01-11 | 2024-01-13 | 2 | 2024-01-14 | 1
T22 | Prepare financial report for Q1 | Charlie | Medium | No Dependency | 2024-01-29 | 2024-01-31 | 2 | 2024-02-02 | 2
T23 | Schedule and conduct weekly team meeting | Charlie | Medium | No Dependency | 2024-01-07 | 2024-01-10 | 3 | 2024-01-11 | 1
T24 | Submit project proposal before deadline | Eve | Urgent | No Dependency | 2024-01-15 | 2024-01-17 | 2 | 2024-01-21 | 4
T25 | Review design documents and provide feedback | Eve | High | No Dependency | 2024-01-16 | 2024-01-22 | 6 | 2024-01-25 | 3
T26 | Update company website homepage with new content | Charlie | Medium | No Dependency | 2024-01-15 | 2024-01-16 | 1 | 2024-01-19 | 3
T27 | Resolve high-priority customer complaints | Alice | Urgent | T3 | 2024-01-20 | 2024-01-25 | 5 | 2024-01-29 | 4
T28 | Analyze user feedback for product enhancements | Eve | High | No Dependency | 2024-01-07 | 2024-01-08 | 1 | 2024-01-10 | 2
T29 | Test new software release for bugs and stability | Eve | High | No Dependency | 2024-01-29 | 2024-02-01 | 3 | 2024-02-03 | 2
T30 | Conduct market research for upcoming product launch | Alice | Medium | T15 | 2024-01-17 | 2024-01-20 | 3 | 2024-01-24 | 4
T31 | Optimize database queries for faster performance | Eve | Urgent | No Dependency | 2024-01-11 | 2024-01-17 | 6 | 2024-01-22 | 5
T32 | Develop machine learning model for sentiment analysis | Eve | Urgent | No Dependency | 2024-01-22 | 2024-01-28 | 6 | 2024-01-31 | 3
T33 | Write and review technical documentation | Charlie | High | No Dependency | 2024-01-05 | 2024-01-08 | 3 | 2024-01-10 | 2
T34 | Improve CI/CD pipeline for automated deployments | Charlie | Low | T6 | 2024-01-10 | 2024-01-17 | 7 | 2024-01-21 | 4
T35 | Monitor server performance and address downtime issues | David | Medium | T34 | 2024-01-03 | 2024-01-09 | 6 | 2024-01-14 | 5
T36 | Train new employees on company policies and procedures | David | Medium | No Dependency | 2024-01-07 | 2024-01-08 | 1 | 2024-01-10 | 2
T37 | Coordinate with vendors for procurement needs | David | Urgent | No Dependency | 2024-01-26 | 2024-01-29 | 3 | 2024-01-29 | 0
T38 | Create social media marketing strategy | Eve | Medium | No Dependency | 2024-01-20 | 2024-01-21 | 1 | 2024-01-24 | 3
T39 | Implement new security patches in infrastructure | Bob | Urgent | No Dependency | 2024-01-22 | 2024-01-25 | 3 | 2024-01-30 | 5
T40 | Refactor legacy code for better maintainability | Bob | Low | No Dependency | 2024-01-10 | 2024-01-15 | 5 | 2024-01-18 | 3
T41 | Fix critical security vulnerability in system | Bob | High | No Dependency | 2024-01-13 | 2024-01-21 | 8 | 2024-01-25 | 4
T42 | Prepare financial report for Q1 | Eve | High | No Dependency | 2024-01-28 | 2024-01-31 | 3 | 2024-02-02 | 2
T43 | Schedule and conduct weekly team meeting | Alice | Medium | T8 | 2024-01-10 | 2024-01-16 | 6 | 2024-01-16 | 0
T44 | Submit project proposal before deadline | Bob | High | T15 | 2024-01-27 | 2024-01-30 | 3 | 2024-02-02 | 3
T45 | Review design documents and provide feedback | Charlie | Low | No Dependency | 2024-01-08 | 2024-01-15 | 7 | 2024-01-18 | 3
T46 | Update company website homepage with new content | Alice | High | T42 | 2024-01-11 | 2024-01-12 | 1 | 2024-01-13 | 1
T47 | Resolve high-priority customer complaints | Bob | Urgent | T29 | 2024-01-20 | 2024-01-28 | 8 | 2024-01-28 | 0
T48 | Analyze user feedback for product enhancements | Alice | Urgent | T39 | 2024-01-17 | 2024-01-21 | 4 | 2024-01-24 | 3
T49 | Test new software release for bugs and stability | Alice | Medium | No Dependency | 2024-01-14 | 2024-01-18 | 4 | 2024-01-23 | 5
T50 | Conduct market research for upcoming product launch | Eve | High | No Dependency | 2024-01-21 | 2024-01-23 | 2 | 2024-01-27 | 4
T51 | Optimize database queries for faster performance | Eve | High | No Dependency | 2024-01-12 | 2024-01-15 | 3 | 2024-01-16 | 1
T52 | Develop machine learning model for sentiment analysis | Eve | High | T35 | 2024-01-17 | 2024-01-19 | 2 | 2024-01-23 | 4
T53 | Write and review technical documentation | Eve | Urgent | No Dependency | 2024-01-12 | 2024-01-20 | 8 | 2024-01-22 | 2
T54 | Improve CI/CD pipeline for automated deployments | Alice | High | T41 | 2024-01-04 | 2024-01-06 | 2 | 2024-01-10 | 4
T55 | Monitor server performance and address downtime issues | Charlie | Urgent | No Dependency | 2024-01-27 | 2024-02-02 | 6 | 2024-02-07 | 5
T56 | Train new employees on company policies and procedures | David | Low | No Dependency | 2024-01-23 | 2024-01-31 | 8 | 2024-02-03 | 3
T57 | Coordinate with vendors for procurement needs | Alice | High | No Dependency | 2024-01-10 | 2024-01-11 | 1 | 2024-01-15 | 4
T58 | Create social media marketing strategy | David | Low | T13 | 2024-01-10 | 2024-01-18 | 8 | 2024-01-20 | 2
T59 | Implement new security patches in infrastructure | Alice | Low | T28 | 2024-01-29 | 2024-02-04 | 6 | 2024-02-07 | 3
T60 | Refactor legacy code for better maintainability | David | Low | No Dependency | 2024-01-16 | 2024-01-23 | 7 | 2024-01-25 | 2
T61 | Fix critical security vulnerability in system | Eve | High | No Dependency | 2024-01-27 | 2024-01-29 | 2 | 2024-01-30 | 1
T62 | Prepare financial report for Q1 | Eve | High | No Dependency | 2024-01-10 | 2024-01-12 | 2 | 2024-01-15 | 3
T63 | Schedule and conduct weekly team meeting | Eve | Medium | No Dependency | 2024-01-24 | 2024-01-27 | 3 | 2024-01-29 | 2
T64 | Submit project proposal before deadline | Eve | Low | No Dependency | 2024-01-13 | 2024-01-18 | 5 | 2024-01-20 | 2
T65 | Review design documents and provide feedback | Eve | Low | T57 | 2024-01-02 | 2024-01-05 | 3 | 2024-01-06 | 1
T66 | Update company website homepage with new content | Alice | High | T5 | 2024-01-20 | 2024-01-26 | 6 | 2024-01-27 | 1
T67 | Resolve high-priority customer complaints | David | Low | No Dependency | 2024-01-05 | 2024-01-11 | 6 | 2024-01-15 | 4
T68 | Analyze user feedback for product enhancements | Charlie | High | No Dependency | 2024-01-06 | 2024-01-11 | 5 | 2024-01-14 | 3
T69 | Test new software release for bugs and stability | Eve | High | No Dependency | 2024-01-15 | 2024-01-17 | 2 | 2024-01-18 | 1
T70 | Conduct market research for upcoming product launch | Eve | High | No Dependency | 2024-01-03 | 2024-01-11 | 8 | 2024-01-14 | 3
T71 | Optimize database queries for faster performance | Bob | Low | No Dependency | 2024-01-28 | 2024-02-05 | 8 | 2024-02-07 | 2
T72 | Develop machine learning model for sentiment analysis | Charlie | Medium | No Dependency | 2024-01-23 | 2024-01-28 | 5 | 2024-02-02 | 5
T73 | Write and review technical documentation | Bob | Medium | T31 | 2024-01-26 | 2024-01-30 | 4 | 2024-02-02 | 3
T74 | Improve CI/CD pipeline for automated deployments | Alice | High | T17 | 2024-01-20 | 2024-01-26 | 6 | 2024-01-26 | 0
T75 | Monitor server performance and address downtime issues | Alice | High | No Dependency | 2024-01-19 | 2024-01-27 | 8 | 2024-01-27 | 0
T76 | Train new employees on company policies and procedures | Bob | Low | No Dependency | 2024-01-12 | 2024-01-14 | 2 | 2024-01-15 | 1
T77 | Coordinate with vendors for procurement needs | Eve | Medium | No Dependency | 2024-01-28 | 2024-01-31 | 3 | 2024-01-31 | 0
T78 | Create social media marketing strategy | Alice | Medium | No Dependency | 2024-01-23 | 2024-01-28 | 5 | 2024-01-29 | 1
T79 | Implement new security patches in infrastructure | Charlie | Low | No Dependency | 2024-01-31 | 2024-02-05 | 5 | 2024-02-09 | 4
T80 | Refactor legacy code for better maintainability | Charlie | Urgent | No Dependency | 2024-01-19 | 2024-01-24 | 5 | 2024-01-28 | 4
T81 | Fix critical security vulnerability in system | Bob | Urgent | T11 | 2024-01-02 | 2024-01-08 | 6 | 2024-01-13 | 5
T82 | Prepare financial report for Q1 | Eve | High | No Dependency | 2024-01-16 | 2024-01-20 | 4 | 2024-01-25 | 5
T83 | Schedule and conduct weekly team meeting | Eve | High | T52 | 2024-01-10 | 2024-01-15 | 5 | 2024-01-18 | 3
T84 | Submit project proposal before deadline | Alice | Medium | No Dependency | 2024-01-07 | 2024-01-10 | 3 | 2024-01-12 | 2
T85 | Review design documents and provide feedback | Eve | Urgent | No Dependency | 2024-01-12 | 2024-01-18 | 6 | 2024-01-22 | 4
T86 | Update company website homepage with new content | Eve | Urgent | No Dependency | 2024-01-08 | 2024-01-12 | 4 | 2024-01-13 | 1
T87 | Resolve high-priority customer complaints | Alice | Urgent | T21 | 2024-01-27 | 2024-02-03 | 7 | 2024-02-05 | 2
T88 | Analyze user feedback for product enhancements | Eve | Medium | T60 | 2024-01-16 | 2024-01-20 | 4 | 2024-01-22 | 2
T89 | Test new software release for bugs and stability | David | Urgent | No Dependency | 2024-01-12 | 2024-01-19 | 7 | 2024-01-19 | 0
T90 | Conduct market research for upcoming product launch | Alice | High | No Dependency | 2024-01-04 | 2024-01-12 | 8 | 2024-01-15 | 3
T91 | Optimize database queries for faster performance | Bob | Low | No Dependency | 2024-01-02 | 2024-01-08 | 6 | 2024-01-12 | 4
T92 | Develop machine learning model for sentiment analysis | Eve | Urgent | No Dependency | 2024-01-25 | 2024-01-30 | 5 | 2024-02-03 | 4
T93 | Write and review technical documentation | Charlie | Low | No Dependency | 2024-01-26 | 2024-01-28 | 2 | 2024-01-30 | 2
T94 | Improve CI/CD pipeline for automated deployments | Eve | Low | No Dependency | 2024-01-17 | 2024-01-20 | 3 | 2024-01-20 | 0
T95 | Monitor server performance and address downtime issues | Alice | Urgent | No Dependency | 2024-01-20 | 2024-01-26 | 6 | 2024-01-30 | 4
T96 | Train new employees on company policies and procedures | Bob | High | T95 | 2024-01-27 | 2024-02-02 | 6 | 2024-02-04 | 2
T97 | Coordinate with vendors for procurement needs | Eve | High | T48 | 2024-01-11 | 2024-01-19 | 8 | 2024-01-24 | 5
T98 | Create social media marketing strategy | Alice | Low | No Dependency | 2024-01-31 | 2024-02-05 | 5 | 2024-02-10 | 5
T99 | Implement new security patches in infrastructure | Eve | Medium | No Dependency | 2024-01-24 | 2024-01-25 | 1 | 2024-01-29 | 4
T100 | Refactor legacy code for better maintainability | David | Urgent | T15 | 2024-01-07 | 2024-01-11 | 4 | 2024-01-11 | 0